## Template Risk Register
GLASGOW CALEDONIAN UNIVERSITY | [9 empty] | SCHOOL/DEPARTMENT
PROJECT NAME
PROJECT RISK REGISTER | [9 empty] | PROJECT VALUE
[10 empty] | OVERALL RESIDUAL PROJECT RISK |  |  |  | B
No. | SPECIFIC RISK |  |  | IMPACT (i.e. severity) | LIKELIHOOD | GROSS RISK SCORE AS PER MATRIX (1 - 16) | MITIGATION ACTIONS, PROCEDURES/CONTROLS IN PLACE | IMPACT (i.e. severity) | LIKELIHOOD | RESIDUAL RISK SCORE AS PER MATRIX (1 - 16) | 1. EARLY WARNING MECHANISMS 2. ACTIONS PLANNED | Timeline | Completed Actions | RISK OWNER
| Provide clear detail of the project risk, and then using the table below evaluate the impact and likelihood of this risk without any controls in place. |  |  | Minor | Unlikely | Cell Populates automatically based on Impact and Likelihood entries | List all mitigating actions, procedures and controls which will then impact on the gross risk score to create a revised residual risk score. | Minor | Unlikely | Cell Populates automatically based on Impact and Likelihood entries | List early warning mechanisms and other planned future actions which enhance the management of this risk, providing timelines where appropriate. | Key Milestone dates for any material events or actions planned | Note Actions completed since last Risk Register review | Name. Should be one individual
1 | [5 empty] | 0 |  |  |  | 0 | Early Warning Mechanisms • Actions Planned •
2 | [5 empty] | 0 |  |  |  | 0
3 | [5 empty] | 0 |  |  |  | 0
4 | [5 empty] | 0 |  |  |  | 0
5 | [5 empty] | 0 |  |  |  | 0
6 | [5 empty] | 0 |  |  |  | 0
7 | [5 empty] | 0 |  |  |  | 0
8 | [5 empty] | 0 |  |  |  | 0
Impact
|  | 0 | Minor | Significant | Serious | Major
| Likelihood | Certain | 4 | 8 | 12 | 16
|  | Probable | 3 | 6 | 9 | 12
|  | Possible | 2 | 4 | 6 | 8
|  | Unlikely | 1 | 2 | 3 | 4
This risk assessment form must be completed and submitted with every Research and Innovation Office
(RIO) Proposal Approval Form for Research & Commercial Proposal authorisation.
[10 empty] | Signed : Principal Investigator |  |  | Date:
[10 empty] | Signed : Associate Dean of Research |  |  | Date:
[10 empty] | Signed : School Dean / Vice-Dean (required if Project value greater than £50k) |  |  | Date:

## Notes to aid Completion
Notes on Completion of Project Risk Register
Notes per Highlighted Cells/Columns on Example Risk Register |  | Additional Points to note while completing a Risk Register
A | Insert total value of Project Funding or Projected Income for full life of project | 1 | The Example Risk Register is provided to highlight some key risks that would consistently be expected to be reflected in a Risk Register. These are provided purely for example purposes and it is expected that these are used as guidelines and not just copied into the relevant Project Risk Register. Each Project Risk Register should be compiled based on the Risks specific to the individual project.
B | Delete the shaded row with instructions, list the Risks sequentially from 1. Delete any template rows that are unused | 2 | There is no right or wrong number of Risks but we would generally expect a minimum of five and a maximum of fifteen depending on the project.
C | Provide a brief succinct description of the Risk identified | 3 | The Gross Risk is the theoretical risk without any of the existing controls, the Residual Risk is the actual risk given the controls in place and, therefore, should be lower than the Gross Risk. The Residual Risk can never be higher than the Gross Risk and if it is the same as the Gross Risk then we are indicating that there are either no mitigating actions or controls or that any controls are having no impact.
D | Input a Gross Likelihood score per the 4x4 Matrix grading of Minor to Major - Drop down menu provided. The Gross Risk is the assumed Risk without any of the controls in place or existing mitigating actions | 4 | The Risk Register should be a live document and reviewed regularly in line with the lifetime and key milestones of the project.
E | Input a Gross Impact score per the 4x4 Matrix grading of Unlikely to Certain - Drop down menu provided. The Gross Risk is the assumed Risk without any of the controls in place or existing mitigating actions | 5 | To delete/add rows, highlight the row, right click and choose either Insert or Delete.
F | Cell calculates automatically based on Likelihood and Impact Scores | 6 | When inputting into a cell and wanting a new line within the cell, hold down the Alt key and then hit Return
G | Provide details of the existing controls and actions which are in place to reduce the likelihood or impact of the Risk identified | 7 | When reviewing the Risk Register it is expected that over time the Actions Planned should move into Controls in Place/Mitigating Actions once completed and contribute towards a potentially lower Residual Risk score.
H | Input a Residual Likelihood score per the 4x4 Matrix grading of Minor to Major - Drop down menu provided. The Residual Risk is the assumed Risk after taking account of all controls in place or existing mitigating actions
I | Input a Residual Impact score per the 4x4 Matrix grading of Minor to Major - Drop down menu provided. The Residual Risk is the assumed Risk after taking account of all controls in place or existing mitigating actions
J | Cell calculates automatically based on Likelihood and Impact Scores
K | Provide details of any Early Warning Mechanisms which would indicate the risk has materialised and any Actions Planned to mitigate against the Risk. The Residual Risk score should not take these planned actions into account, however, once they are in place, they would be assumed to move into the Mitigating Actions column and contribute to reducing the Residual Risk score
L | Provide details of any key timelines/dates in relation to the noted Actions Planned
M | Provide details of actions completed since last review - have these now been moved to Controls in Place/Mitigating Actions and should the Risk score change?
N | Risk Owner - Should be one individual where possible

## Generic Example Risk Register
GLASGOW CALEDONIAN UNIVERSITY | [9 empty] | SCHOOL/DEPARTMENT |  | GSBS/EBE/SHLS/GCU London/SWBE/YUNUS etc.
[10 empty] | PROJECT NAME |  | Example Research Project
PROJECT RISK REGISTER | [9 empty] | PROJECT VALUE |  | A
[10 empty] | OVERALL RESIDUAL PROJECT RISK |  |  |  | B
B | C |  |  | D | E | F | G | H | I | J | K | L | M | N
No. | SPECIFIC RISK |  |  | IMPACT (i.e. severity) | LIKELIHOOD | GROSS RISK SCORE AS PER MATRIX (1 - 16) | MITIGATION ACTIONS, PROCEDURES/CONTROLS IN PLACE | IMPACT (i.e. severity) | LIKELIHOOD | RESIDUAL RISK SCORE AS PER MATRIX (1 - 16) | 1. EARLY WARNING MECHANISMS 2. ACTIONS PLANNED | Timeline | Completed Actions | RISK OWNER
| Provide clear detail of the project risk, and then using the table below evaluate the impact and likelihood of this risk without any controls in place. |  |  | Minor | Unlikely | Cell Populates automatically based on Impact and Likelihood entries | List all mitigating actions, procedures and controls which will then impact on the gross risk score to create a revised residual risk score. | Minor | Unlikely | Cell Populates automatically based on Impact and Likelihood entries | List early warning mechanisms and other planned future actions which enhance the management of this risk, providing timelines where appropriate. | Key Milestone dates for any material events or actions planned | Note Actions completed since last Risk Register review | Name. Should be one individual
1 | Reputational risk that GCU provides an incorrect Research conclusion that is based on flawed assumptions or incorrect/incomplete data |  |  | Major | Probable | 12 | • Peer review of data sample techniques and project conclusions • Appropriately qualified staff in position | Major | Unlikely | 4 | Early Warning Mechanisms • Issues collecting appropriate data samples • Departure of key personnel from project • Partner institutions missing deadlines and submitting incomplete data Actions Planned • Regular communication with funding body to highlight any concerns with project delivery |  |  | PI
2 | Risk that GCU does not meet the contracted deliverables or timelines in line with agreed Project parameters |  |  | Major | Certain | 16 | • Peer review of data sample techniques and project conclusions • Appropriately qualified staff in position • Project timeline and milestones agreed with funder • Regular project meetings with all stakeholders to review progress against agreed timelines | Major | Unlikely | 4 | Early Warning Mechanisms • Recruitment cycle factored into project timelines • Partner institutions missing deadlines and submitting incomplete data Actions Planned • Risk of third party providing key data highlighted to funder as impacting timelines |  |  | PI
3 | Risk that GCU as Lead partner fails to manage the risks and outputs of other contributing partner institution |  |  | Major | Probable | 12 | • Signed agreements with Partner Institutions outlining agreed outputs and timelines • Regular communication with Partners to highlight potential risks/issues that have arisen • Diligence carried out on key partners where appropriate | Significant | Unlikely | 2 | Early Warning Mechanisms • Partner Institution departing from project • Partner institutions missing deadlines and submitting incomplete data Actions Planned • Risk of third party providing key data highlighted to funder as impacting timelines |  |  | PI
4 | Risk that key personnel leave project with insufficient handover or no alternative personnel/skills in place |  |  | Major | Possible | 8 | • Contingency plans in place if key personnel leave Institution or fall ill • Appropriately qualified staff in position | Serious | Possible | 6 | Early Warning Mechanisms • Absence of key personnel • Inability to recruit appropriately qualified staff Actions Planned •Agree any contingency plans and impact on timelines with key stakeholders |  |  | PI
5 | Risk that GCU is unable to collect sufficient sample data to meet the project deliverables |  |  | Major | Possible | 8 | • Research parameters outlined in project contract with appropriate mitigating procedures in place • Signed contract/agreements in place with key third party data providers • Diligence carried out on key partners where appropriate | Significant | Possible | 4 | Early Warning Mechanisms • Third party partners missing agreed deadlines Actions Planned • Regular communication with funders and stakeholders to highlight any issues with agreed timelines or outputs |  |  | PI
6 | Risk that GCU does not recover all of agreed funding due to non-approved expenditure or spend outwith the terms of the funding, leading to an overall deficit to the Budgeted project contribution |  |  | Major | Possible | 8 | • Agreed funding contract in place • Project Budget approved through RIE and Finance • Appropriate procurement procedures in place to ensure purchases are in line with agreed expenditure • All reporting requirements factored into Project plan and responsibilities agreed | Significant | Possible | 4 | Early Warning Mechanisms • Deviation from agreed budgeted expenditure highlighted by Finance Actions Planned • Regular review of Project actual spend v Budgets |  |  | PI
7 | Risk of data breach and sensitive information not being treated in line with legislative requirements |  |  | Major | Probable | 12 | • GCU Data Management and Information Security Policy • All project staff members appropriately trained in Information Security and Data Management • All non GCU project partners with access/control over data are covered by appropriate compliance procedures to ensure equal standards with GCU data management and Information Security | Major | Unlikely | 4 | Early Warning Mechanisms • Data sharing issues highlighted during contractual negotiations with project partners Actions Planned • Regular communication to personnel and partners to reiterate data management compliance procedures |  |  | PI
9 | Specific Project Risk |  |  | F: 0; OVERALL RESIDUAL PROJECT RISK J: 0
10 | Specific Project Risk |  |  | F: 0; OVERALL RESIDUAL PROJECT RISK J: 0
8 | Health and Safety Risk to individuals in relation to foreign travel/work carried out at 3rd party premises |  |  | Serious | Probable | 9 | • GCU Health and Safety Policy • GCU travel Risk Assessment • Appropriate Diligence carried out on any 3rd party contractors/partners to assure appropriate insurance and risk assessments are in place. | Serious | Unlikely | 3 | Early Warning Mechanisms • Data sharing issues highlighted during contractual negotiations with project partners Actions Planned • Regular communication to personnel and partners to reiterate data management compliance procedures |  |  | PI
Impact
|  | 0 | Minor | D: Significant; E: Serious; F: Major
| Likelihood | Certain | 4 | D: 8; E: 12; F: 16
|  | Probable | 3 | D: 6; E: 9; F: 12
|  | Possible | 2 | D: 4; E: 6; F: 8
|  | Unlikely | 1 | D: 2; E: 3; F: 4
This risk assessment form must be completed and submitted with every Research, Innovation
and Enterprise (RIE) Proposal Approval Form for Research & Commercial Proposal authorisation.
[10 empty] | Signed : Principal Investigator |  |  | Date:
[10 empty] | Signed : Associate Dean of Research |  |  | Date:
[10 empty] | Signed : Executive Dean / Head of Function |  |  | Date: